## Risk Treatment Plan
UnityTrust Bank — Risk Treatment Plan (Mitigate)
ISO/IEC 27001:2022 ISMS Implementation ¦ Shehzad Ahmad ¦ Information Security & Risk Management
Risk ID | Asset ID | Asset Name | Risk Description | L | I | Risk Score | Risk Level | Treatment | ISO 27001 Ref | Mitigating Control(s) | Control Owner | Target Completion | Residual Risk | Status
RSK-01 | AST-01 | Core Banking Platform | Unauthorized access or malware compromise of the core banking platform disrupting transaction processing and customer trust. | 4 | 5 | 20 | Critical | Mitigate | 8.7 / 8.8 | Deploy a centralized malware management dashboard and implement a formal patch management SLA with defined remediation timelines. | Head of IT Operations | 1 Month | Medium | In Progress
RSK-02 | AST-02 | Mobile Banking App | Credential theft via phishing or man-in-the-middle attacks compromising customer mobile banking sessions. | 4 | 4 | 16 | High | Mitigate | 8.5 | Enforce certificate pinning and mandatory multi-factor authentication for all mobile banking sessions. | Digital Channels Manager | 2 Months | Medium | Planned
RSK-03 | AST-03 | Internet Banking Portal | Web application attacks (SQL injection/XSS) or credential stuffing compromising internet banking accounts. | 4 | 4 | 16 | High | Mitigate | 8.28 / 8.29 | Adopt secure coding guidelines and introduce dedicated security testing (SAST/DAST) before every release. | Digital Channels Manager | 3 Months | Medium | Planned
RSK-04 | AST-04 | USSD Banking Service | SIM swap fraud and USSD session interception leading to unauthorized transactions. | 3 | 3 | 9 | Medium | Mitigate | 8.24 | Implement session-level encryption and step-up verification for high-value USSD transactions. | Digital Channels Manager | 3 Months | Low | Planned
RSK-05 | AST-05 | Contact Center / CRM System | Social engineering of contact center agents leading to unauthorized disclosure of customer data. | 2 | 3 | 6 | Medium | Mitigate | 6.3 | Deliver mandatory annual security awareness training with social engineering simulations for contact center staff. | Customer Service Manager | 2 Months | Low | Planned
RSK-06 | AST-06 | ATM Switch | Card skimming and ATM jackpotting malware resulting in financial fraud and service disruption. | 4 | 5 | 20 | Critical | Mitigate | 8.8 / 8.9 | Upgrade ATM switch software to the latest secure version and implement continuous vulnerability scanning. | Payments Operations Manager | 1 Month | Medium | In Progress
RSK-07 | AST-07 | POS / Merchant Acquiring | POS malware and merchant-side fraud compromising card transaction data. | 3 | 4 | 12 | High | Mitigate | 8.7 | Mandate PCI-DSS compliant POS terminals and deploy malware detection at merchant endpoints. | Payments Operations Manager | 3 Months | Medium | Planned
RSK-08 | AST-08 | RTGS / ACH Payment Gateway | Payment fraud, manipulation, or denial-of-service attack against the interbank settlement gateway. | 4 | 5 | 20 | Critical | Mitigate | 8.16 | Implement real-time transaction anomaly detection and establish 24/7 SOC monitoring for the payment gateway. | Payments Operations Manager | 1 Month | Medium | In Progress
RSK-09 | AST-09 | SIEM Platform | Missed security incidents due to incomplete system onboarding to the SIEM platform. | 3 | 3 | 9 | Medium | Mitigate | 8.15 | Onboard all remaining critical systems to the SIEM and establish a minimum logging standard. | SOC Manager | 2 Months | Low | Planned
RSK-10 | AST-10 | Transaction Monitoring (AML/Fraud) | Evasion of AML and fraud detection due to outdated detection rule sets, enabling financial crime. | 3 | 5 | 15 | High | Mitigate | 5.7 / 8.16 | Establish a quarterly rules-tuning process supported by a dedicated threat intelligence feed. | Compliance / Fraud Manager | 2 Months | Medium | Planned
RSK-11 | AST-11 | DLP System | Sensitive data exfiltration bypassing under-tuned data loss prevention policies. | 3 | 4 | 12 | High | Mitigate | 8.12 | Retune DLP policies to cover all sensitive data types identified under the classification scheme. | Information Security Manager | 2 Months | Medium | Planned
RSK-12 | AST-12 | KYC Repository | Unauthorized access to customer PII due to absence of formal data classification, risking a data breach. | 4 | 5 | 20 | Critical | Mitigate | 5.12 / 5.34 | Implement a formal data classification and labelling scheme and enforce a documented privacy policy. | Compliance Manager | 2 Months | Medium | In Progress
RSK-13 | AST-13 | Data Warehouse | Unauthorized data access resulting from broad, infrequently reviewed access rights. | 3 | 4 | 12 | High | Mitigate | 5.18 | Introduce a quarterly access recertification process for all data warehouse users. | BI / Analytics Manager | 2 Months | Medium | Planned
RSK-14 | AST-14 | BI / Analytics Platform | Data leakage through cloud-hosted analytics workloads lacking a formal cloud security policy. | 2 | 2 | 4 | Low | Mitigate | 5.23 | Adopt a formal cloud security policy covering all BI and analytics cloud workloads. | BI / Analytics Manager | 3 Months | Low | Planned
RSK-15 | AST-15 | Credit Decision Engine (ML Models) | Model manipulation or data poisoning of the ML credit scoring engine undermining lending decisions. | 2 | 4 | 8 | Medium | Mitigate | 8.25 / 8.29 | Establish a formal model governance and validation process, including adversarial testing before deployment. | Credit Risk Manager | 4 Months | Low | Planned
RSK-16 | AST-16 | Open Banking API Gateway | API abuse or unauthorized third-party access due to weak partner-side security requirements. | 3 | 4 | 12 | High | Mitigate | 5.20 | Embed mandatory security SLAs and enforce API rate-limiting and authentication controls in all partner agreements. | IT Architecture Manager | 3 Months | Medium | Planned
RSK-17 | AST-17 | DR Site & Backup Infrastructure | Failed failover during a disaster event due to untested DR and backup procedures. | 2 | 5 | 10 | Medium | Mitigate | 5.30 / 8.14 | Establish and execute a scheduled DR failover testing programme at least twice a year. | IT Infrastructure Manager | 3 Months | Low | Planned
RSK-18 | AST-18 | PKI / Key Management System | Cryptographic key compromise due to the absence of a formal, documented cryptographic policy. | 2 | 5 | 10 | Medium | Mitigate | 8.24 | Document and implement a formal cryptographic policy covering the full key management lifecycle. | Information Security Manager | 2 Months | Low | Planned
RSK-19 | AST-19 | Identity & Access Management (IAM) | Privilege escalation via orphaned accounts not covered by centralized IAM across all SaaS tools. | 3 | 4 | 12 | High | Mitigate | 5.16 / 8.2 | Extend centralized IAM coverage to all SaaS and third-party tools with automated deprovisioning. | Information Security Manager | 3 Months | Medium | Planned
RSK-20 | AST-20 | Privileged Access Management (PAM) | Misuse of privileged administrative access due to an unformalized account review process. | 3 | 4 | 12 | High | Mitigate | 8.2 | Formalize a quarterly privileged account review and enable session recording for administrative activity. | Information Security Manager | 2 Months | Medium | In Progress
RSK-21 | AST-21 | Employee Endpoints (Laptops/Desktops) | Malware infection or data loss from unpatched, lost, or stolen endpoint devices. | 3 | 3 | 9 | Medium | Mitigate | 8.1 | Define and enforce an endpoint hardening baseline with mandatory full-disk encryption. | IT Support Manager | 2 Months | Low | Planned
RSK-22 | AST-22 | Network Infrastructure | Network intrusion or distributed denial-of-service attack enabled by infrequent firewall rule review. | 3 | 4 | 12 | High | Mitigate | 8.20 | Establish a quarterly firewall rule review cycle and subscribe to a DDoS protection service. | Network Manager | 2 Months | Medium | Planned
RSK-23 | AST-23 | Data Center Facility | Unauthorized physical access at branch locations due to inconsistent physical security standards. | 1 | 4 | 4 | Low | Mitigate | 7.1 / 7.2 | Standardize physical access control and visitor logging across all branch locations. | IT Infrastructure Manager | 3 Months | Low | Planned
RSK-24 | AST-24 | IT & Security Staff (Privileged Users) | Insider threat or successful phishing due to the lack of an annual security awareness refresher. | 3 | 4 | 12 | High | Mitigate | 6.3 | Launch a mandatory annual security awareness and phishing-simulation programme for all staff. | CISO / Head of IT | 2 Months | Medium | Planned
RSK-25 | AST-25 | Customer PII & Financial Records | Data breach or regulatory non-compliance exposure due to the absence of a formal privacy policy. | 4 | 5 | 20 | Critical | Mitigate | 5.34 | Develop and implement a formal privacy and data protection policy aligned with regulatory requirements. | Data Protection Officer | 2 Months | Medium | In Progress
RSK-26 | AST-26 | Third-Party Fintech Partners / Vendors | Third-party data breach or SLA non-compliance due to the absence of a supplier risk assessment process. | 3 | 4 | 12 | High | Mitigate | 5.19 / 5.20 | Implement a formal supplier security risk assessment process and embed security SLAs in all vendor contracts. | Vendor Management | 3 Months | Medium | Planned

## Methodology & Legend
Methodology & Rating Legend
UnityTrust Bank ¦ Risk Treatment Plan
Risk Treatment Option Selected: Mitigate
Mitigate | ISO/IEC 27001:2022 recognizes four treatment options: Mitigate, Avoid, Transfer, and Accept. UnityTrust Bank has adopted Mitigate for every identified risk in this plan - reducing likelihood and/or impact through the implementation of specific Annex A controls, rather than avoiding, transferring, or accepting the risk.
Likelihood (L) and Impact (I) Scale (1-5)
Score | Description
1 | Rare / Negligible - very unlikely to occur or minimal consequence
2 | Unlikely / Minor - low probability or limited consequence
3 | Possible / Moderate - could occur; noticeable operational impact
4 | Likely / Major - expected to occur; significant financial or regulatory impact
5 | Almost Certain / Severe - highly probable; critical impact on operations or trust
Risk Score Formula
Risk Score = L x I | Example: RTGS/ACH Payment Gateway rated Likelihood=4, Impact=5 -> Risk Score = 20 -> Risk Level = Critical.
Risk Level Thresholds (based on Risk Score)
Risk Level | Score Range
Critical | 20 - 25
High | 12 - 19
Medium | 6 - 11
Low | 1 - 5
Notes
• | Risks in this plan are drawn from the Asset Identification & Threat Register and the Gap Analysis Report, ensuring traceability across all three deliverables.
• | Residual Risk reflects the expected risk level after the mitigating control has been fully implemented and verified.
• | Target Completion timelines are aligned to risk severity: Critical/High risks are prioritized for near-term remediation.
• | Status reflects the state of control implementation at the time of this report: Planned or In Progress.